## Sheet1
TCS3 Project Schedule | 2003 | [11 empty] | 2004 | [11 empty] | 2005
| Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
[5 empty] | Year 1 | [12 empty] | Year 2 | [11 empty] | Year 3 (5 months)
Prelimiary Design (2 months) | bar: 2003 May to 2003 Jun
Procurement (4 months) | bar: 2003 July to 2005 Jan
Development and Testing (10 months) | bar: 2003 May to 2005 Jan
Observatory Preparation (3 months) | bar: 2003 July to 2005 Jan
Installation at observatory (3 months) | bar: 2003 July to 2005 Jan
Testing and Engineering runs (3 months) | bar: 2005 Feb to 2005 Apr
Operational shakedown ( 6 months) | bar: 2005 May to 2005 Oct
Pre-Project Milestones
April 2000 - started writing description of work, estimated cost and manpower requirement need for tcs upgrade. Document revised numerious times. Eventually it was submitted as proposal to NASA on June 2001.
Grant Awarded June 2002
Project Starts - May 2003
TCS Programmer Hired - May 2003 to Oct 2005
Design Milestones
Project Overview - May 22, 2003 | bar: 2003 May
Conceptual Design Review - June 26, 2003 | bar: 2003 Jun to 2003 July
Task Milestones
0. Project Overview - May 22, 2003 | bar: 2003 May
1. Conceptual Design - July, 2003 | bar: 2003 Jun to 2003 July
2. Build TCS3 computer and test servo controller | bar: 2003 Aug to 2004 Feb
3. Positional feedback for RA, Dec, and Dome | bar: 2003 Oct to 2004 Feb
4. Install initial MCC replacement at summit. | bar: 2004 Feb to 2004 May
5. TO Panel | bar: 2004 Apr to 2004 Jun
6. Drive RA, Dec, and Dome | bar: 2004 July to 2004 Oct
7. Observers Paddles | bar: 2004 Oct to 2004 Dec
8. Daytime test | bar: 2005 Jan to 2005 Mar
9. Night Engineering | bar: 2005 Apr