## Sheet1
Action Item # | Description | Assigned to | Required Completion Date | Completion Date | Comment
1 | Look at spare motors vs. original. Are they acceptable? Run simulation also to see if there any concerns. | E. Warmbier | 2007-12-08 | 2007-12-13
2 | Have Ed Sousa look over the review material. | E. Warmbier | 2008-01-01 |  | I have discussed some aspects with Ed before, but I will sit down with him and discuss it in more detail.
3 | Put up SIMULINK models on website | E. Warmbier | 2007-11-30 | 2007-12-13
4 | Put up comparison files on website | E. Warmbier | 2007-11-30 | 2007-12-13
5 | Talk to George about maintenance documentation, spares, troubleshooting, etc. | E. Warmbier | 2007-03-08 | 2007-11-29 | Spoke with George and created a list of some things he would like to see for TCS. Of course, this is an ongoing process. File is listed on website in same directory as this file.
Date Created: 11/29/07
Author: E. Warmbier
DESCRIPTION
Action items from November TCS Modeling Review. Attendees: George, Darryl, Alan, Tony, Peter, Eric T., Tim